Agile Exercise

Using the Agile methodology to Organise a Party. Generate:

- a Backlog List

- List of 2 sprites with allocations from Backlog

- WBS & Gnatt Chart for whole project

Include duration for each item and a Resources List with costs

Backlog List:

The backlog consists of all the tasks needed to organize the party. Tasks are prioritized based on importance.

Venue and Date:

Research and book a venue

Confirm date and time

Prepare invitation list

Food and Drinks

Plan the menu

Arrange catering or cook food

Purchase beverages

Decorations and Ambience

Choose a theme

Buy decorations

Set up lighting and music system

Entertainment

Hire a DJ or create a playlist

Arrange party games/activities

Prepare a photo booth or props

Guest Communication

Design and send out invitations

Confirm guest attendance (RSVPs)

Logistics

Arrange tables, chairs, and other furniture

Set up a cleanup crew

Day of the Party

Set up the venue

Welcome guests

Ensure the event runs smoothly

----------------------------------------------------------------------------------------------------------

Sprints:

Sprint 1: Preparation and Initial Planning

Duration: 1 week
Backlog Items Allocated:

Research and book a venue

Confirm date and time

Prepare invitation list

Choose a theme

Design invitations

Team Allocation:

Organizer A: Venue, date, and invitations

Organizer B: Theme and guest list

------------------------------------------------------------------------------------------------------------

Sprint 2: Execution and Finalization

Duration: 1 week
Backlog Items Allocated:

Arrange catering

Buy decorations

Arrange entertainment (DJ/games)

Set up logistics (tables, chairs)

Finalize guest list and confirm RSVPs

Team Allocation:

Organizer A: Food, drinks, and decorations

Organizer B: Entertainment and logistics

Work Breakdown Structure (WBS)

1. Planning

Research and book venue
Confirm date and time
Choose a theme
Design and send invitations
Prepare guest list

2. Procurement

Purchase decorations
Arrange food and drinks
Organize tables, chairs, and furniture

3. Setup

Decorate the venue
 	Set up lighting and music
 	Arrange seating and tables

4. Party Execution

Welcome guests
 	Coordinate entertainment (games, music)
 	Ensure food and drinks are served

5. Post-Party

Clean up
 	Evaluate success and gather feedback

----------------------------------------------------------------------------------------------------------------

Gnatt Chart:

| Task | Duration | Start Date | End Date | Dependency |
| --- | --- | --- | --- | --- |
| Planning | 7 days | Day 1. | Day 7. | None |
| Procurement | 3 days | Day 8 | Day 10 | Planning. |
| Setup | 2 days | Day 11 | Day 12 | Requirement Analysis |
| Party Execution | 1 day.. | Day 13 | Day 13 | Design |
| Post-Party | 1 day. | Day 14 | Day 14 | Boil Water |

Resource List with Costs:

| Resource | Unit Cost. | Quantity Used. | Total Cost |
| --- | --- | --- | --- |
| Venue Booking | £500 per event. | 1 | £500 |
| Invitations | £0.50 each | 50 | £25 |
| Decorations | £100 total. | 1 | £100 |
| Catering/Food | £10 per person | 50 | £500 |
| Beverages | £2 per person. | 50 | £100.. |
| DJ/Music | £300 per event | 1 | £300 |
| Party Games | £50 total. | 1 | £50 |
| Cleanup Crew | £50 per hour | 2hours | £100 |

Total Estimated Cost: £1,675