Work Breakdown Structure Exercise

Each group must choose from one of the following small projects:

Projects:

- Organise an event (night out or birthday party)

- Decorate bedroom

- Build a shed for the garden

- A project of your choice? Run it by your lecturer first 😊

Once the group has discussed and decided on a project each group must:

- Produce a WBS list (include work packages / tasks)

- Produce a Resource list to include activity, name of resource, duration and cost.

At least one member of the group should fill in the tables below and upload to ‘WBS Exercise Submission’ on canvas.

WBS List

Project Name: Organize a Birthday Party

| Stage | Activity (description) | Duration (mins, hours, days) | predecessor |
| --- | --- | --- | --- |
| Stage 1 | Define party theme and objectives | 1 hour | - |
| Stage 1 | Set party date and time | 30 minutes | - |
| Stage 1 | Book the venue (if required) | 1 hour | Set party date and time |
| Stage 1 | Prepare guest list | 1 hours | Define party theme and objectives |
| Stage 1 | Send invitations to guests | 1 hours | Prepare guest list |
| Stage 1 | Order food and drinks | 4 hours | Send invitations to guests |
| Stage 1 | Arrange entertainment (DJ, games, etc.) | 1 hours | Order food and drinks |
| Stage 1 | Decorate venue | 4 hours | Book the venue |
| Stage 1 | Set up the party area (tables, chairs, etc.) | 2 hours | Decorate venue |
| Stage 1 | Clean up after the event | 4 hours | Event completion |

Resource List

| Activity | Resource Name | Duration | Cost |
| --- | --- | --- | --- |
| Define party theme and objectives | Party Planner | 1 hour | £30 |
| Set party date and time | Party Planner. | 30 minutes | £10 |
| Book the venue | Event Coordinator. | 2 hours | £100 |
| Prepare guest list | Party Planner. | 1 hour. | £20 |
| Send invitations to guests | Party Planner | 1 hour. | £15 |
| Order food and drinks | Catering Service | 1 hour | £200 |
| Arrange entertainment | Entertainment Co.. | 4 hours | £150 |
| Decorate venue | Decoration Team | 2 hours | £50 |
| Set up the party area | Party Crew. | 3 hours | £40 |
| Clean up after the event | Party Crew. | 4 hours | £60 |

Once complete upload to canvas ‘WBS exercise submission’.