Assessment Task 2

Case Study

The company

Ellnot is a fashion company which currently operates their business through their outlet on the high street. Through acquiring the stock from various suppliers, Ellnot owns a large collection of fashion items which are currently displayed in their store. Aimed at the female market, the company sells various top-of-the-range products.

They include:

- tops

- skirts

- trousers

- jackets

- dresses

- knitwear

- petticoats

- plus-size garments

- vintage items

- scarves

- hats

as well as accessories including bags, purses and jewellery.

The owners want to expand their business by launching a web gallery which will allow them to extend their marketing reach by displaying their fashion products over the internet.

The project is to start on the 1st June and to be completed by the end of August.

The owners have allocated a budget of £30,000 for the total cost of the project. The software package used to develop the web gallery is negotiable.

Site layout and navigation:

The web gallery needs to be aesthetically pleasing and functional, giving the various web pages a slick and professional look to attract a wider audience.

The web gallery must be secure, robust and accessible.

As the web gallery will be the main focus of the business, the pages need to be easy to navigate and with a fast response time.

Any page of the site should be accessible from any other page via the navigation menu. Users should always be aware of the page that they are currently viewing.

The placement of the navigation menu and the company banner, including the logo, should remain consistent throughout the entire web gallery.

Links to social media sites should appear on all pages.

Display products:

The customer should be able to view all the items. They can do that by either selecting the individual category or using ‘All items’ option.

There should be a brief description of each item including:

- price

- size

and a number of photos showing the item from various angles.

Graphics should be lightweight to allow for fast loading of the page.

Text should be used over graphics whenever possible.

Search for products:

The Search option should allow for free text to be typed in.

A sorted list of all the products that match the search text will appear for the user to select from.

While searching for products, the user should be able to sort the displayed products.

Options available are to sort by product type, price and size.

Note: Please see below for Assessment Instructions

Assessment Instructions:

Applying the Agile approach to the given scenario and focusing on the Analysis and Design phases, your task is to produce the following:

Task 1:

Create a product backlog for the above scenario which lists all requirements:

| ID | Functional Requirement |
| --- | --- |
| F1 | The web gallery should allow customers to view all items in individual categories. |
| F2 | Users should have an "All Items" option to view the entire product collection. |
| F3 | Each product should have a brief description, including price and size. |
| F4 | Products should have multiple photos from various angles. |
| F5 | Customers should be able to use a free-text search to find products. |
| F6 | Search results should be sortable by product type, price, and size. |
| F7 | A consistent navigation menu and company banner should appear on all pages. |
| F8 | Links to social media should be visible on every page. |

| ID | Non-Functional Requirement |
| --- | --- |
| NF1 | The web gallery must be aesthetically pleasing and professional in design. |
| NF2 | Pages should load quickly to enhance the user experience. |
| NF3 | The site should be robust, secure, and accessible. |
| NF4 | Navigation between pages should be smooth, and users should always know their location within the site. |
| NF5 | Graphics should be lightweight to improve page loading times. |
| NF6 | The website must be compatible with mobile and desktop browsers. |

Task 2:

Create at least one user story for one sprint. The user story should include the ‘who’, ‘what’ and the ‘why’ of a requirement in a simple and concise way:

| As a….. | I want to….. | So that…. |
| --- | --- | --- |
| As a customer interested in fashion | I want to search for products by typing keywords in a search bar and sort results by price, size, or type, | So that I can quickly find the items I’m looking for without browsing the entire catalogue. |

Task 3:

Create a Roadmap for each Sprint Planning and Initial Design

| Date: | Sprint 1: (June 1 - June 30): | Sprint 2: (July 1 - July 31) | Sprint 3 (August 1 - August 31) - Final Version |
| --- | --- | --- | --- |
| Version | Alpha | Beta | Final |
| Goal | Finalize the layout, navigation structure, and basic functionality. | Implement the core functionality, including product displays and search features. | Testing, debugging, and polishing the web gallery. |
| Requirements | 1.Design the consistent navigation menu and company banner (F7, NF4). 2.Plan product category pages and display layout (F1, F2, NF1). 3.Add links to social media (F8). | 1. Display all products with descriptions, prices, and photos (F3, F4). 2. Implement search and sorting functionality (F5, F6). | 1. testing and debugging (NF3). 2.Optimize loading times and improve responsiveness (NF2, NF5, NF6). 3.Deploy and launch the website. |
| Has Goal been met? | Pending at the end of Sprint 1 | Pending at the end of Sprint 2 | To be completed by August 31 |

Task 4:

Provide evidence to show how you plan to track the progress of your project ( you should include at least one sprint) and any other tasks associated with using the Agile Approach.

Please add Gantt chart Image below (screenshot):

Progress Tracking Plan

- Progress will be tracked using Agile Boards (Kanban) to monitor task completion in real time.

- Key tools for tracking:

  - User Stories: Break down requirements into smaller tasks.

  - Daily Standups: Short daily meetings to update on progress.

  - Burndown Chart: Visualize the remaining tasks against the timeline.

| Task | Start Date. | End Date | Duration |
| --- | --- | --- | --- |
| Requirement Gathering | June 1 | June 5 | 5 days |
| Design Navigation Menu | June 6 | June 12. | 7 days. |
| Plan Product Categories. | June 13. | June 19 | 7 days |
| Development of Display | June 20 | July 15. | 25 days |
| Implement Search Features | July 16 | July 25 | 10 days |
| Testing and debugging | July 26 | August 5 | 10 days |
| Deployment and Launch | August 6. | August 31 | 25 days |

You will also have to upload your project libre file to canvas as evidence. If you are unable to use project libre then I will accept a WBS List and Person / non-Person Lists.

Note: Once above is complete please submit to Canvas ‘Agile Assessment Submission’.

Task 5:

You must evaluate / reflect on your performance by completing / submitting an evaluation form (available on canvas)

Once the project is completed, use the provided evaluation form to reflect on:

- What went well: Identify areas of success (e.g., on-time delivery, effective sprint planning).

- Challenges faced: Discuss hurdles (e.g., design or functionality issues).

- Improvements for future projects: Propose adjustments for better execution.

Resources and Costs:

| Resource | Unit Cost (£) | Quantity. | Total Cost (£) |  |
| --- | --- | --- | --- | --- |
| Web Developer | £300/day | 30 days | £9,000 |  |
| Designer | £250/day | 20 days | £5,000. |  |
| Hosting and Domain | £100/month | 3 months | £300 |  |
| Graphic Assets | £1,000 one-time | 1 | £1,000. |  |
| Testing Team | £200/day | 10 days. | £2,000 |  |
| Marketing Budget | £3,000 one-time. | 1. | £3,000 |  |
| Miscellaneous | - | - | £1,000. |  |

Total Cost: £21,300

Note: There is a separate submission for the Evaluation Document.